## Sheet1
SETHI COUTURE UPDATES
Reference | Initiative | Page | Platform | Date Identified | Priority | Status
1 | Font overlay over hero image; Font is too high and top of font is cropped off | Homepage | Mobile | 2019-11-11 | High | Done
2 | you want clear CTA in the Hero image | Homepage | Mobile & Desktop | 2019-11-11 | High | Done
3 | Spacing between hero image and 2 subcategories | Homepage | Mobile | 2019-11-11 | Medium | Done
4 | Legibility of white font over image | Homepage | Mobile & Desktop | 2019-11-11 | Medium | Done
5 | There isn’t anything that looks like shoppable product above the fold; Information hierarchy | Homepage | Mobile | 2019-11-11 | High | Done
6 | Too much copy for stacks | Homepage | Mobile and Desktop | 2019-11-11 | Medium | Done
7 | CTA button placement | homepage | Mobile | 2019-11-11 | Low | Done
8 | Surprised to see necklaces merchandised here | Homepage | Mobile & Desktop | 2019-11-11 | Low | Done
9 | Gap in necklace image and product name | Homepage | Mobile | 2019-11-11 | Medium | Done
10 | Product name, descriptor, price, image size | Homepage | Mobile & Desktop | 2019-11-11 | Medium | Done
11 | Avoid showing the same product in multiple colors on homepage | Homepage | Mobile & Desktop | 2019-11-11 | Low | Done
12 | See more after the end of the product features | Homepage | Mobile & Desktop | 2019-11-11 | Medium | Done
13 | Email capture CTA takes up a lot of real estate | Homepage | Mobile & Desktop | 2019-11-11 | Low | Done
14 | Visit our stores is confusing | Homepage | Mobile & Desktop | 2019-11-11 | Low | Done
15 | Instagram images don't have any context | Homepage | Mobile & Desktop | 2019-11-11 | Low | Done
16 | huge gap between IG images and then footer information | Homepage | Mobile & Desktop | 2019-11-11 | Low | Done
17 | Site navigation footer: info hierarchy, site map, social icons | Homepage | Mobile & Desktop | 2019-11-11 | Low | Done
18 | Site navigation top: Search, log in, basket, | Homepage | Mobile | 2019-11-11 | High | Done
19 | Promo banner (free shipping/lifetime guarantee) | Homepage | Mobile & Desktop | 2019-11-11 | High | Done
20 | Navigation bar: information hierarchy | Homepage | Mobile | 2019-11-11 | Medium | Done
21 | Navigation Bar: background color and font color | Homepage | Mobile | 2019-11-11 | Medium | Done
22 | Top level categories should be exposed | Homepage | Desktop | 2019-11-11 | Medium | Done
23 | Login - need context and reason why | Nav | Mobile & Desktop | 2019-11-11 | Medium
24 | Search display | Nav | Desktop | 2019-11-11 | Medium | Done
25 | Search results display | Search | Mobile | 2019-11-11 | High | Done
26 | Search display results - product images | Search | Mobile & Desktop | 2019-11-11 | Medium | Done
27 | Search results - product description | Search | Mobile and Desktop | 2019-11-11 | Medium | Done
28 | Search results sorts | Search | Mobile and Desktop | 2019-11-11 | Low
29 | Search results filters | Search | Mobile and Desktop | 2019-11-11 | Low
30 | Spacing for white space and product name | Product | Mobile | 2019-11-12 | Low | Done
31 | Alt images | Product | Mobile and Desktop | 2019-11-12 | Low | Done
32 | Style number location | Product | Mobile and Desktop | 2019-11-12 | Low | Done
33 | Loves/Favorite/Wishlist feature | Product | Mobile and Desktop | 2019-11-12 | Low | Done
34 | Sizes Listed | Product | Mobile and Desktop | 2019-11-12 | Low | Done
35 | CTA to buy | Product | Mobile and Desktop | 2019-11-12 | High | Done
36 | Extra spacing | Product | Mobile and Desktop | 2019-11-12 | Low | Done
37 | Product description | Product | Mobile and Desktop | 2019-11-12 | High | Done
38 | Pinterest reference | Product | Mobile and Desktop | 2019-11-12 | Low | Done
39 | Upsell/Cross-sell merchandise | Product | Mobile and Desktop | 2019-11-12 | Low | Done
40 | Missing header | Category | Mobile | 2019-11-12 | Medium | Done
41 | SEO friendly description for category | Category | Mobile and Desktop | 2019-11-12 | Medium | Done
42 | Font consistency | Terms | Mobile and Desktop | 2019-11-12 | Low | Done
43 | In Contact Us - create an email form. | Contact Us | Mobile and Desktop |  | Medium | Done
44 | Need to list out and price out individual rings in the stack | Sethi Stacks | Mobile and Desktop |  | Medium
45 | Product Name, price to fit on 2 separate lines and without dash | Product Collection | Mobile and Desktop |  | High | Done
46 | Buy it Now button | Product | Mobile and Desktop |  | Medium | Done
47 | Variants missing for PS collection | PS Collection | Mobile and Desktop |  | High | Done
48 | Variants missing for some stack bands and rings | Stack Bands | Mobile and Desktop |  | High | Done
49 | Variants missing for PS collection gold chains | PS Collection | Mobile and Desktop |  | Low | Done
50 | Add a product care page | New | Mobile and Desktop |  | Low | Done
| Add google analytics linking to exisiting account |  |  |  | High | Done
| Transfer domain from Jumpline hosting for sethicouture.com to Shopify |  |  |  | High | Done
51 | Checkout | Checkout | Mobile and Desktop | 2019-11-18 | High | Done
46 | Checkout | Basket | Mobile and Desktop | 2019-11-18 | Medium | Done
47 | Checkout | Basket | Mobile and Desktop | 2019-11-18 | Medium
49 | Checkout | Checkout | Mobile | 2019-11-18 | Medium
53 | Checkout | Basket | Mobile and Desktop |  | Medium
43 | Checkout | Nav | Mobile and Desktop | 2019-11-18 | Low | Done
44 | Checkout | Product page | Mobile and Desktop | 2019-11-18 | Low
45 | Checkout | Basket | Mobile and Desktop | 2019-11-18 | Low | Done
48 | Checkout | Basket | Mobile and Desktop | 2019-11-18 | Low
50 | Checkout | Checkout | Mobile and Desktop | 2019-11-18 | Low
52 | Checkout | Basket/Checkout | Mobile and Desktop | 2019-11-18 | Low