## Sheet1
admin Features | date | status | Comment
Setup admin Panel /student panel /teacher Panel | 2020-08-04 | done | kindly Elborate teacher panel in detail
teacher (crud) | 2020-08-05
student(crud) | 2020-08-05
assigne studen to teacher | 2020-08-06
change status of student block/active or inactive etc | 2020-08-06
steup Role and permession | 2020-08-07
Class Scheduling | 2020-08-10
payment Integration |  |  | kindly elborate payment plan scenario
Student Dashboard
Student Signup and register | 2020-08-11
submit assignment | 2020-08-11
online Quiz | 1 day perdict |  | Depand on teacher panel
student timetable | 1day
student added in coursce
studetn view all courcess
student view teacher